September XX, 2025

Mr. Steven Marfitano, P.E.

City and County of Denver

Department of Transportation and Infrastructure

201 W. Colfax Avenue, Denver, CO 80202

RE: 	W Alameda Lane Reduction

City and County of Denver, CO

Master Contract Alfresco No.: 202056606

Task Order No. 2

Task Order Alfresco No.: PO-00120141

Amendment #4

Dear Mr. Marfitano:

Kimley-Horn and Associates, Inc. (the “Consultant” or “Kimley-Horn”) is pleased to submit this Amendment to modify the agreement dated August 15, 2022 (the “Agreement”) with the City and County of Denver (the “Client” or “CCD”) for the W Alameda Lane Reduction Project for the Department of Transportation and Infrastructure in Denver, Colorado (the “Project”).  Kimley-Horn has entered into the Agreement with Client for the furnishing of professional services, and the parties now desire to amend the Agreement.

Therefore, it is mutually agreed that the Agreement is amended to include additional services for the project as set forth below.  The parties ratify the terms and conditions of the Agreement not inconsistent with this Amendment, all of which are incorporated by reference.

# Project Understanding

City desires update of previous analysis and final design efforts for an alternative consisting of one (1) westbound through travel lane, one (1) turn lane/median, and two (2) eastbound through travel lanes

Intersection improvements at Alameda Ave & Franklin St included in 2021 Pedestrian Program Intersection Improvements PRJ-10002820/310/50/501100 dated 7/18/2022 prepared by Muller Engineering Company are to be designed and constructed by others and will not be included in the Alameda Lane Reduction final design plans

City desires a revised approach to the traffic analysis, safety analysis, final design, and public engagement tasks as noted in the scope of services below

# Scope of Services

## Revised Task 1	Project Management and meetings

### Project Coordination/Meetings

Kickoff Meeting (up to one [1])

City Coordination Meetings (up to nine [9])

Stakeholder Meetings (up to two [2])

Project Oversight and Management (assuming a nine [9] month schedule)

## REVISED Task 2	data collection

### Traffic Counts

24-Hour ADT Counts (up to three [3] locations)

Peak hour turning movement counts (AM and PM) at Virginia Ave & Downing St intersection

### Crash Data

Kimley-Horn will gather recent crash reports provided by DOTI

## Revised Task 3	Traffic and Safety Analysis and Evaluation

### Traffic Analysis

Utilize previously developed model; no re-calibration is anticipated or included

Re-evaluate alternative identified in Project Understanding

Analysis to consider and confirm:

Anticipated traffic diversion, queueing, delay and impacts to the project corridor, project intersections, and adjacent facilities

Individual intersection spot treatment/interventions to ensure recommendations are consistent with crash and traffic conditions

Recommended corridor traffic signal timing

Existing and proposed intersection conditions and recommendations at Virginia Ave & Downing St

### Crash and Safety Analysis

Review of crash patterns, crash reduction factors (CRFs) and validation of draft DOTI analysis

Summary of specific mitigations for crash patterns and confirmation of individual intersection treatment/interventions

intersection treatment/interventions

Summarize in memorandum justifying each component of the final project and noting anticipated impacts.

## Revised Task 5	Public Engagement

Engagement efforts to be led by the City Community Designers with minimal support from Kimley-Horn

Public Meeting not anticipated

Kimley-Horn to support with content revisions for website and print materials

Kimley-Horn to provide Spanish translation for engagement materials

## Revised Task 6	Final Design

Previously prepared final design plans to be modified based on the Project Understanding and analysis completed in Revised Task 3

Final design plans are anticipated to consist of the following sheets:

Cover Sheet (up to one [1] sheet)

General Notes (up to four [4] sheets)

CCD Standard Details (up to one [1] sheet)

Summary of Approximate Quantities (up to one [1] sheet)

Tabulations (up to one [1] sheet)

Signing and Striping Removal Plan (up to six [6] sheets)

Signing and Striping Plan (up to seven [7] sheets)

Details (up to four [4] sheet)

Revised Engineer’s Opinion of Probable Construction Costs (EOPCC)

Revised Specifications

60%, 90%, 100% submittals; address up to two (2) rounds of reasonable consolidated CCD ER comments

# Additional Services

Traffic signal modification plans

Travel time runs

Re-calibration of traffic model

# Schedule

Traffic and Crash/Safety Analysis – Approximately 2-3 months

Plans, Specifications, and Estimates – Approximately 4-6 months

# Fee and Expenses

Kimley-Horn will perform the services described in the new and revised tasks outlined below for the additional labor fee as follows:

| Task | Description | Additional Fee |
| --- | --- | --- |
| Revised Task 1 | Project Management and Meetings | $XXX |
| Revised Task 2 | Data Collection | $XXX |
| Revised Task 3 | Traffic and Safety Analysis and Evaluation | $XXX |
| Revised Task 5 | Public Engagement | $XXX |
| Revised Task 6 | Final Design | $XXX |
| Total New Amendment #4 Fees |  | $XXX |

# Closure

We appreciate the opportunity to provide these services to you and are excited to continue to support the City and County of Denver on this project.  Please contact me if you have any questions.

Sincerely,

KIMLEY-HORN AND ASSOCIATES, INC.

By:	Matt Ciarkowski, P.E.

Project Manager